## Lessons Learned Log
| LESSONS LEARNED LOG |  |  | https://bit.ly/3b6NNVB
1) | PROJECT NAME |  | DOCUMENT NUMBER | DATE OF LAST UPDATE | DATE OF FAILURE
2) | PARTICIPANTS
3) | PROJECT SUMMARY
4) | DESCRIPTION OF PROJECT FAILURE
5) | POSSIBLE CAUSES OF PROJECT FAILURE
6) | SIGNS OF IMPENDING FAILURE
7) | WHAT WENT WRONG?
8) | KEY POTENTIAL RISKS
| ACTION PLAN | RESPONSE KEY
|  | MITIGATE | AVOID | TRANSFER | ACCEPT
# | IDENTIFIED RISKS | BEST RESPONSE TO RISK | ACTION ITEM | OWNER | DEADLINE
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16

## Lessons Learned CWL0003-01
| LESSONS LEARNED LOG |  |  | https://bit.ly/3b6NNVB
1) | PROJECT NAME |  | DOCUMENT NUMBER | DATE OF LAST UPDATE | DATE OF FAILURE
| Spring Drawing Clarity |  | CWL0003-01 | 2023-07-26 | 2023-07-25
2) | PARTICIPANTS
Sunny, Matthew Eaton, Pato Guevara, Josie, David
3) | PROJECT SUMMARY
Parts were to be cut and welded with specifications required by the customer that Cryowest would translate from the customer.
4) | DESCRIPTION OF PROJECT FAILURE
Drawings submitted to the team were not clear, leading to longer cuts on parts, incorrect welds, and other issues.
5) | POSSIBLE CAUSES OF PROJECT FAILURE
Drawings are not standardized to a specific design document requirement.
6) | SIGNS OF IMPENDING FAILURE
Drawings are not standardized to a specific design document requirement.
7) | WHAT WENT WRONG?
Waste of Transportation (constant back and forth with parts), Waste of Motion (constant movement of inspectors), Waste of Waiting (waiting for parts to be corrected due to drawing), Waste of Defects (recutting and rewelding parts to correct issues with drawing translations)
8) | KEY POTENTIAL RISKS
How can we assure all drawings for Cryowest have the same standards of communication no matter the drawer?
| ACTION PLAN | RESPONSE KEY
|  | MITIGATE | AVOID | TRANSFER | ACCEPT
# | IDENTIFIED RISKS | BEST RESPONSE TO RISK | ACTION ITEM | OWNER | DEADLINE
1 | Lack of Standardization | MITIGATE | Design a "design document" to assure all drawings are consistent no matter who draws them. | Leadership | N/A
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16

## Lessons Learned Log CWL0003-02
| LESSONS LEARNED LOG |  |  | https://bit.ly/3b6NNVB
1) | PROJECT NAME |  | DOCUMENT NUMBER | DATE OF LAST UPDATE | DATE OF FAILURE
| Mainspring Crashing Q&A |  | CWL0003-02 | 2023-07-26 | 2023-07-26
2) | PARTICIPANTS
Brandon Wall, Matthew Eaton
3) | PROJECT SUMMARY
In order to assure parts could be delivered on time, Quality Assurance had to measure all parts and submit a FAIR document as "proof of concept."
4) | DESCRIPTION OF PROJECT FAILURE
Changes to delivery were not communicated until late in the project, which caused an issue with resource time. Inspector is hourly, so it also limited the times available for other inspection as needed.
5) | POSSIBLE CAUSES OF PROJECT FAILURE
Change of delivery methods and times, no proper change control and communication to anticipate the issue.
6) | SIGNS OF IMPENDING FAILURE
More frequent questions and concerns regarding the status of parts and FAIRs without prompting.
7) | WHAT WENT WRONG?
Waste of Transportation (parts moving around to different stages across the factory), Waste of Motion (constant moving back and forth of inspectors and staff), Waste of "compressed" Overprocessing [AKA "Crashing"] (Conducting full measurements within a limited time frame), Poor communication, poor change management
8) | KEY POTENTIAL RISKS
How can we assure proper change control can be enacted for future projects?
How can we reduce the need for crashing a phase?
| ACTION PLAN | RESPONSE KEY
|  | MITIGATE | AVOID | TRANSFER | ACCEPT
# | IDENTIFIED RISKS | BEST RESPONSE TO RISK | ACTION ITEM | OWNER | DEADLINE
1 | Change Control | MITIGATE | Enact proper Change Control Board for projects to assure changes are vetted and communicated properly | Leadership | N/A
2 | Reduce Crashing | MITIGATE | Better Project Management Scheduling philosophies and including all departments. | Project Manager | N/A
3
4
5
6
7
8
9
10
11
12
13
14
15
16