## Lessons Learned Log
| LESSONS LEARNED LOG |  |  | https://bit.ly/3b6NNVB
1) | PROJECT NAME |  | DOCUMENT NUMBER | DATE OF LAST UPDATE | DATE OF FAILURE
2) | PARTICIPANTS
3) | PROJECT SUMMARY
4) | DESCRIPTION OF PROJECT FAILURE
5) | POSSIBLE CAUSES OF PROJECT FAILURE
6) | SIGNS OF IMPENDING FAILURE
7) | WHAT WENT WRONG?
8) | KEY POTENTIAL RISKS
| ACTION PLAN | RESPONSE KEY
|  | MITIGATE | AVOID | TRANSFER | ACCEPT
# | IDENTIFIED RISKS | BEST RESPONSE TO RISK | ACTION ITEM | OWNER | DEADLINE
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16

## Lessons Learned CWL0001-01
| LESSONS LEARNED LOG |  |  | https://bit.ly/3b6NNVB
1) | PROJECT NAME |  | DOCUMENT NUMBER | DATE OF LAST UPDATE | DATE OF FAILURE
| SpaceX Subassembly Wrench |  | CWL0001-01 | 2023-07-24 | 2023-07-17
2) | PARTICIPANTS
John McCartney, Cesar Martinez, Ricardo Martinez
3) | PROJECT SUMMARY
Subassembly stage for the SpaceX parts
4) | DESCRIPTION OF PROJECT FAILURE
When putting on the valves in the subassembly area, the tema discovered the wrench they intended to use did not have clearance to tighten the fittings.
5) | POSSIBLE CAUSES OF PROJECT FAILURE
Incorrect assumptions of parts and tools required for proceeding. There was also not an assessment of the drawing beforehand and clear inspection of the valves to assure they would comply with the drawing.
6) | SIGNS OF IMPENDING FAILURE
No parts arrived for inspection nor did we consult drawings.
7) | WHAT WENT WRONG?
Assumptions based on previous works, assumption of talents and skills, assumption of "process matching," assumption of schedule crashing (taking more than the alloted people to work on project in the area)
8) | KEY POTENTIAL RISKS
Incorrect tools
Incorrect fittings
| ACTION PLAN | RESPONSE KEY
|  | MITIGATE | AVOID | TRANSFER | ACCEPT
# | IDENTIFIED RISKS | BEST RESPONSE TO RISK | ACTION ITEM | OWNER | DEADLINE
1 | Incorrect tools | MITIGATE | Assess the drawings and assess tools in the area to make sure we have everything in place. | Subassembly Lead | N/A
2 | Incorrect fittings | MITIGATE | Assess the drawings and assess tools in the area to make sure we have everything in place. | Subassembly Lead | N/A
3
4
5
6
7
8
9
10
11
12
13
14
15
16

## Lessons Learned CWL0001-02
| LESSONS LEARNED LOG |  |  | https://bit.ly/3b6NNVB
1) | PROJECT NAME |  | DOCUMENT NUMBER | DATE OF LAST UPDATE | DATE OF FAILURE
| SpaceX Subassembly Fittings |  | CWL0001-02 | 2023-07-24 | 2023-07-17
2) | PARTICIPANTS
John McCartney, Cesar Martinez, Ricardo Martinez
3) | PROJECT SUMMARY
Subassembly stage for the SpaceX parts
4) | DESCRIPTION OF PROJECT FAILURE
While setting up for the valve fittings, subassembly attempted to put on the hook valve with two brass fittings. When they attempted to tighten it on the main body, the hook valve did not have clearance.
5) | POSSIBLE CAUSES OF PROJECT FAILURE
Incorrect assumptions of parts and tools required for proceeding. There was also not an assessment of the drawing beforehand and clear inspection of the valves to assure they would comply with the drawing.
6) | SIGNS OF IMPENDING FAILURE
No parts arrived for inspection nor did we consult drawings.
7) | WHAT WENT WRONG?
Assumption based on knowledge, assumption based on previous works, assumption based on "process matching."
8) | KEY POTENTIAL RISKS
Parts were not inspected properly
Drawing was not vetted for parts order
Materials were not vetted for correct parts.
| ACTION PLAN | RESPONSE KEY
|  | MITIGATE | AVOID | TRANSFER | ACCEPT
# | IDENTIFIED RISKS | BEST RESPONSE TO RISK | ACTION ITEM | OWNER | DEADLINE
1 | No Parts Inspections | MITIGATE | Parts for new projects should be flagged properly for future projects | Manufacturing Engineer | N/A
2 | Vetting drawings | MITIGATE | Parts with tight clearance should be vetted before the drawing is submitted via PMO | Manufacturing Engineer | N/A
3 | Vetting materials | MITIGATE | Materials should be vetted before the drawing is submitted via PMO | Manufacturing Engineer | N/A
4
5
6
7
8
9
10
11
12
13
14
15
16

## Lessons Learned CWL0001-03
| LESSONS LEARNED LOG |  |  | https://bit.ly/3b6NNVB
1) | PROJECT NAME |  | DOCUMENT NUMBER | DATE OF LAST UPDATE | DATE OF FAILURE
| SpaceX Weighing for Shipments |  | CWL0001-03 | 2023-07-24 | 2023-07-20
2) | PARTICIPANTS
Matthew Eaton, Cesar Martinez, Brandon Wall, Max Hinckley
3) | PROJECT SUMMARY
To assure proper shipping methods are in place, parts must be weighed.
4) | DESCRIPTION OF PROJECT FAILURE
After placing completed parts on carts, it was determined they had to be removed from their carts to weigh. This would have led to serious safety issues.
5) | POSSIBLE CAUSES OF PROJECT FAILURE
Assumption the parts would be easy to remove from the carts without understanding the weight involved.
6) | SIGNS OF IMPENDING FAILURE
No consultation of the specifications before items were placed on standard plastic carts. Not acquiring flat carts with adjustable height (please see lessons learned for shipping).
7) | WHAT WENT WRONG?
Assumption of manpower, assumption of ease, assumption of "previous methods," lack of safety protocol
8) | KEY POTENTIAL RISKS
Carts to assist in heavy part movement
Weighing standards for shipping
Consulting incorrect weight generated from drawings
| ACTION PLAN | RESPONSE KEY
|  | MITIGATE | AVOID | TRANSFER | ACCEPT
# | IDENTIFIED RISKS | BEST RESPONSE TO RISK | ACTION ITEM | OWNER | DEADLINE
1 | Flat Bed Carts | ACCEPT | For future heavy items, it would be best to consult for flat bed adjustable carts. | Project Management | N/A
2 | Proper Weighing | MITIGATE | Using pallet jack on plastic carts was not safe. Proper heavy duty scale for future use. | Facilities | N/A
3 | Drawing Consultation | MITIGATE | Refer to previous information from CAD model and drawings for weight consideration | Manufacturing Engineer | N/A
4
5
6
7
8
9
10
11
12
13
14
15
16

## Lessons Learned CWL0001-04
| LESSONS LEARNED LOG |  |  | https://bit.ly/3b6NNVB
1) | PROJECT NAME |  | DOCUMENT NUMBER | DATE OF LAST UPDATE | DATE OF FAILURE
| SpaceX Orbital Weld Flanges |  | CWL0001-04 | 2023-07-24 | 2023-07-17
2) | PARTICIPANTS
Cesar Martinez, Ken Kostlan, Ricardo Martinez
3) | PROJECT SUMMARY
Part would have to go through the cold tests before being packed
4) | DESCRIPTION OF PROJECT FAILURE
After finishing the final touches on the welding, it was determined there were not proper connections for the orbital welds to conduct the cold test.
5) | POSSIBLE CAUSES OF PROJECT FAILURE
When the drawing was created, there was no auditing of the parts required in the subassembly area. This also is reflected in some of the other issues that appeared in the subassembly area (please see CWL0001-01).
6) | SIGNS OF IMPENDING FAILURE
The lack of consultation and staging of these items, making the connectors from scratch once they arrived at the subassembly location.
7) | WHAT WENT WRONG?
Assumption of process, assumption of time, assumption of resources, assumption of "process matching," assumption of bandwidth.
8) | KEY POTENTIAL RISKS
Subassembly area was not assessed or audited for proper parts.
Parts were created on the fly at the moment of the parts arrival, not before they were needed.
| ACTION PLAN | RESPONSE KEY
|  | MITIGATE | AVOID | TRANSFER | ACCEPT
# | IDENTIFIED RISKS | BEST RESPONSE TO RISK | ACTION ITEM | OWNER | DEADLINE
1 | Area assessments | MITIGATE | When a new project is submitted, it will be critical to audit each area for parts and tools | Project Manager | N/A
2 | Parts creation | AVOID | Submit request for making parts well before they are needed. | Manufacturing Engineer | N/A
3
4
5
6
7
8
9
10
11
12
13
14
15
16

## Lessons Learned CWL0001-05
| LESSONS LEARNED LOG |  |  | https://bit.ly/3b6NNVB
1) | PROJECT NAME |  | DOCUMENT NUMBER | DATE OF LAST UPDATE | DATE OF FAILURE
| SpaceX Leak Checking Subassembly |  | CWL0001-05 | 2023-07-24 | 2023-07-20
2) | PARTICIPANTS
Cesar Martinez, John McCartney, Ricardo Martinez
3) | PROJECT SUMMARY
SpaceX project to be leak checked at each stage
4) | DESCRIPTION OF PROJECT FAILURE
While leak checking for final stages, subassembly team struggled to leak check with standard equipment. Access to specific areas (under valves) made things more complex, leading to crashing the stage with multiple people.
5) | POSSIBLE CAUSES OF PROJECT FAILURE
Not auditing the leak checking and detection areas to assure proper equipment was available (extensions, tips, etc).
6) | SIGNS OF IMPENDING FAILURE
No audits of the areas
7) | WHAT WENT WRONG?
Assumption of process, assumption of time, assumption of resources, assumption of "process matching," assumption of bandwidth.
8) | KEY POTENTIAL RISKS
Inability to leak check properly.
Escaped leak check
| ACTION PLAN | RESPONSE KEY
|  | MITIGATE | AVOID | TRANSFER | ACCEPT
# | IDENTIFIED RISKS | BEST RESPONSE TO RISK | ACTION ITEM | OWNER | DEADLINE
1 | Incorrect accessories | MITIGATE | When a new project is submitted, it will be critical to audit each area for parts and tools | Project Manager | N/A
2 | Escaped leaker | MITIGATE | When a new project is submitted, it will be critical to audit each area for parts and tools | Project Manager | N/A
3
4
5
6
7
8
9
10
11
12
13
14
15
16

## Lessons Learned CWL0001-06
| LESSONS LEARNED LOG |  |  | https://bit.ly/3b6NNVB
1) | PROJECT NAME |  | DOCUMENT NUMBER | DATE OF LAST UPDATE | DATE OF FAILURE
| SpaceX Valve Placement |  | CWL0001-06 | 2023-07-24 | 2023-07-20
2) | PARTICIPANTS
Sunny
3) | PROJECT SUMMARY
SpaceX parts will have complex welding process due to the angles of tubing and placement of valves.
4) | DESCRIPTION OF PROJECT FAILURE
While attempting to weld interior, welding tech expressed their frustration with the valve placement via the drawing. The project was completed, but it was a chore to weld together.
5) | POSSIBLE CAUSES OF PROJECT FAILURE
Overcomplexity of drawing, overprocessing of parts, complete audit of drawing and skills.
6) | SIGNS OF IMPENDING FAILURE
When putting together the parts to weld, it was determined how much of a struggle it would be to get things welded properly.
7) | WHAT WENT WRONG?
Assumption of skills, assumption of "process matching," assumption of time
8) | KEY POTENTIAL RISKS
Overcomplexity of drawings
Overprocessing of welds
Missing fixtures (using 2x4s instead of actual fixtures)
Missing guidance and feedback
| ACTION PLAN | RESPONSE KEY
|  | MITIGATE | AVOID | TRANSFER | ACCEPT
# | IDENTIFIED RISKS | BEST RESPONSE TO RISK | ACTION ITEM | OWNER | DEADLINE
1 | Overcomplexity | MITIGATE | Parts with tight clearance should be vetted before the drawing is submitted via PMO | Project Manager | N/A
2 | Overprocessing | MITIGATE | Processing should be vetted before the drawing is submitted via PMO | Project Manager | N/A
3 | Missing Fixtures | MITIGATE | When a new project is submitted, it will be critical to audit each area for parts and tools | Project Manager | N/A
4 | Missing Guidance | MITIGATE | Project Manager and associates should be more interactive with technicians on the floor. | Project Manager | N/A
5
6
7
8
9
10
11
12
13
14
15
16

## Lessons Learned CWL0001-07
| LESSONS LEARNED LOG |  |  | https://bit.ly/3b6NNVB
1) | PROJECT NAME |  | DOCUMENT NUMBER | DATE OF LAST UPDATE | DATE OF FAILURE
| SpaceX No Tube Stub |  | CWL0001-07 | 2023-07-24 | 2023-07-17
2) | PARTICIPANTS
Sunny
3) | PROJECT SUMMARY
SpaceX parts will have complex welding process due to the angles of tubing and placement of valves.
4) | DESCRIPTION OF PROJECT FAILURE
While welding the internal structure, the technician expressed concerns over tube stubs. While changing from the 8 valve tube to the 4 valve tube, technician prepared as if the internals were the same length.
5) | POSSIBLE CAUSES OF PROJECT FAILURE
Human error, no follow up from officiating team, no closure steps processed for previous project.
6) | SIGNS OF IMPENDING FAILURE
No clear definition and no follow up.
7) | WHAT WENT WRONG?
Assumption of skills, assumption of process, assumption of "process matching," assumption of knowledge, assumption of clarity.
8) | KEY POTENTIAL RISKS
Processing the incorrect parts
Lack of follow up from officiating team
Unclear instructions
| ACTION PLAN | RESPONSE KEY
|  | MITIGATE | AVOID | TRANSFER | ACCEPT
# | IDENTIFIED RISKS | BEST RESPONSE TO RISK | ACTION ITEM | OWNER | DEADLINE
1 | Incorrect parts for build | MITIGATE | Assure that operators and technicians are following the correct procedures | Supervisor and Officiating teams | N/A
2 | Lack of Follow Up | MITIGATE | Physically debrief and close out previous projects before proceeding, going over "gameplan" to assure no waste of processing | Supervisor and Officiating teams | N/A
3 | Unclear Instructions | MITIGATE | Physically debrief and close out previous projects before proceeding, going over "gameplan" to assure no waste of processing | Supervisor and Officiating teams | N/A
4
5
6
7
8
9
10
11
12
13
14
15
16

## Lessons Learned CWL0001-08
| LESSONS LEARNED LOG |  |  | https://bit.ly/3b6NNVB
1) | PROJECT NAME |  | DOCUMENT NUMBER | DATE OF LAST UPDATE | DATE OF FAILURE
| SpaceX Body Roundness |  | CWL0001-08 | 2023-07-24 | 2023-06-25
2) | PARTICIPANTS
Matthew Eaton, Brandon Wall
3) | PROJECT SUMMARY
Exterior parts for SpaceX were to be cut in-house.
4) | DESCRIPTION OF PROJECT FAILURE
When parts were delivered, QA expressed concerns over deburring (please see CWL0001-09). Once parts were delivered to welding, technician pointed out parts were slightly out of round. Technician would be able to cover up the issue with proper welding.
5) | POSSIBLE CAUSES OF PROJECT FAILURE
Tightness of clamp used while cutting
6) | SIGNS OF IMPENDING FAILURE
Inability to check roundness due to size and lack of methods.
7) | WHAT WENT WRONG?
Assumption of quality, assumption of process, assumption of "process matching," assumption of skills
8) | KEY POTENTIAL RISKS
Roundness issues
Lack of tools to measure larger parts
| ACTION PLAN | RESPONSE KEY
|  | MITIGATE | AVOID | TRANSFER | ACCEPT
# | IDENTIFIED RISKS | BEST RESPONSE TO RISK | ACTION ITEM | OWNER | DEADLINE
1 | Roundness issues | AVOID | Size of part is issue. Rounder tool needs extreme leverage to fix anything after issue. | Quality Inspector | N/A
2 | Lack of Tools | MITIGATE | Assess what tools are needed during PM phase and assure these items are available | Project Management | N/A
3
4
5
6
7
8
9
10
11
12
13
14
15
16

## Lessons Learned CWL0001-09
| LESSONS LEARNED LOG |  |  | https://bit.ly/3b6NNVB
1) | PROJECT NAME |  | DOCUMENT NUMBER | DATE OF LAST UPDATE | DATE OF FAILURE
| SpaceX Flange Issues |  | CWL0001-09 | 2023-07-24 | 2023-06-24
2) | PARTICIPANTS
Trisha, Veronica Martinez, Matthew Eaton, Brandon Wall
3) | PROJECT SUMMARY
Off-the-shelf flanges were shipped out to Cryowest
4) | DESCRIPTION OF PROJECT FAILURE
Flanges were delayed from vendor, which was not reflected in the schedule to account for. Vendor insisted they would arrive, but were still delayed. Nearly prompted a redesign of project which would have greatly delayed (with approval from customer).
5) | POSSIBLE CAUSES OF PROJECT FAILURE
Not checking in with vendor on status, not following up with other vendors, not vetting backups.
6) | SIGNS OF IMPENDING FAILURE
Lack of communication within the team and from vendor.
7) | WHAT WENT WRONG?
Assumption of skills, assumption of process, assumption of "process matching," assumption of distance, assumption of time, assumption of clarity
8) | KEY POTENTIAL RISKS
Redesign of project.
Delay in part delivery.
Backup vendors not in place.
| ACTION PLAN | RESPONSE KEY
|  | MITIGATE | AVOID | TRANSFER | ACCEPT
# | IDENTIFIED RISKS | BEST RESPONSE TO RISK | ACTION ITEM | OWNER | DEADLINE
1 | Redesign of project | AVOID | Have a few vendors as options for parts in future. This will help avoid redesign and delay | Project Management | N/A
2 | Delay in part delivery | MITIGATE | Have a few vendors as options for parts in future. This will help avoid redesign and delay | Project Management | N/A
3 | Backup vendors not in place | MITIGATE | Have a few vendors as options for parts in future. This will help avoid redesign and delay | Project Management | N/A
4
5
6
7
8
9
10
11
12
13
14
15
16

## Lessons Learned CWL0001-10
| LESSONS LEARNED LOG |  |  | https://bit.ly/3b6NNVB
1) | PROJECT NAME |  | DOCUMENT NUMBER | DATE OF LAST UPDATE | DATE OF FAILURE
| SpaceX Changes in Inspection |  | CWL0001-10 | 2023-07-24 | 2023-06-24
2) | PARTICIPANTS
Matthew Eaton, Pato Guevara, Jon Glommen, Brandon Wall, Max Hinckley
3) | PROJECT SUMMARY
Parts to be inspected for every stage completed
4) | DESCRIPTION OF PROJECT FAILURE
During the welding process, production manager expressed concern that quality assurance was not inspecting part after every weld. This was not brought to the attention of quality, but after assessing there was not much for quality to inspect to match the demand from production.
5) | POSSIBLE CAUSES OF PROJECT FAILURE
Lack of clarity in definition of what expectations are required, lack of involvement with departments in project, lack of communication
6) | SIGNS OF IMPENDING FAILURE
Many stages were completed without letting the QA team know about their completion.
7) | WHAT WENT WRONG?
Assumption of clarity, assumption of process, assumption of "process matching," assumption of responsibility
8) | KEY POTENTIAL RISKS
Missed quality assurance issues
Incomplete communication with departments
Incomplete project requirements
| ACTION PLAN | RESPONSE KEY
|  | MITIGATE | AVOID | TRANSFER | ACCEPT
# | IDENTIFIED RISKS | BEST RESPONSE TO RISK | ACTION ITEM | OWNER | DEADLINE
1 | Missed QA Issues | AVOID | All requirements should be addressed at start of project for each department | Project Manager | N/A
2 | Incomplete Communication | MITIGATE | All departments should be involved with start of project to assure they can succeed | Project Manager | N/A
3 | Incomplete Requirements | MITIGATE | All requirements should be written out and agreed upon at start of project. | Project Manager | N/A
4
5
6
7
8
9
10
11
12
13
14
15
16

## Lessons Learned CWL0001-11
| LESSONS LEARNED LOG |  |  | https://bit.ly/3b6NNVB
1) | PROJECT NAME |  | DOCUMENT NUMBER | DATE OF LAST UPDATE | DATE OF FAILURE
| SpaceX Drawing Interpretation |  | CWL0001-11 | 2023-07-24 | 2023-06-29
2) | PARTICIPANTS
Matthew Eaton, Max Hinckley, Brandon Wall
3) | PROJECT SUMMARY
All requirements are driven by the drawings provided by the engineer and project manager.
4) | DESCRIPTION OF PROJECT FAILURE
While attempting to address the changes in QA requirements (see CWL0001-10), QA had a hard time interpreting the requirements as needed. Other departments also had problems processing and seeking clarity for drawings, relying on PM and Engineer to clarify.
5) | POSSIBLE CAUSES OF PROJECT FAILURE
Drawing focused on the drawer, not the people who are building.
6) | SIGNS OF IMPENDING FAILURE
People seeking clarity, searching for answers without getting them.
7) | WHAT WENT WRONG?
Assumption of skills, assumption of process, assumption of "process matching," assumption of knowledge
8) | KEY POTENTIAL RISKS
Missing requirements
Phantom specifications
Poor communications
| ACTION PLAN | RESPONSE KEY
|  | MITIGATE | AVOID | TRANSFER | ACCEPT
# | IDENTIFIED RISKS | BEST RESPONSE TO RISK | ACTION ITEM | OWNER | DEADLINE
1 | Missing Requirements | Avoid | Drawings should be vetted by the departments before they are finalized by the customer | Project Manager | N/A
2 | Phantom Specifications | Avoid | All requirements should be written out and agreed upon at start of project. | Project Manager | N/A
3 | Poor Communications | MITIGATE | All departments should be involved with start of project to assure they can succeed | Project Manager | N/A
4
5
6
7
8
9
10
11
12
13
14
15
16

## Lessons Learned CWL0001-12
| LESSONS LEARNED LOG |  |  | https://bit.ly/3b6NNVB
1) | PROJECT NAME |  | DOCUMENT NUMBER | DATE OF LAST UPDATE | DATE OF FAILURE
| SpaceX Logistics for shipping |  | CWL0001-12 | 2023-07-24 | 2023-07-24
2) | PARTICIPANTS
Alberto, Matt, Matthew Eaton
3) | PROJECT SUMMARY
Final parts will be packed into crates and processed for pick up from customer.
4) | DESCRIPTION OF PROJECT FAILURE
Due to logistics windows, customer is likely to provide a window of 12-4 for pick up. Logistics companies tend to show up on the earlier side of this window to assure their drivers are not stuck in traffic. This project runs a possibility to not be ready by the 12pm start window typically provided (pending confirmation from customers).
5) | POSSIBLE CAUSES OF PROJECT FAILURE
Inability to get processes completed and delivered to shipping by Monday, 7/24/2023 and giving the team time to pack into crate without risking their health.
6) | SIGNS OF IMPENDING FAILURE
Typical patterns provided by outside logistics teams
7) | WHAT WENT WRONG?
Assumption of ease, assumption of process, assumption of "process matching," assumption of communication, assumption of skills
8) | KEY POTENTIAL RISKS
Logistics company arrives too early
Parts are not packed by the time logistics company arrives
Risk to health and safety due to time crunch
| ACTION PLAN | RESPONSE KEY
|  | MITIGATE | AVOID | TRANSFER | ACCEPT
# | IDENTIFIED RISKS | BEST RESPONSE TO RISK | ACTION ITEM | OWNER | DEADLINE
1 | Early arrival | AVOID | To assure proper time, reduce time spent processing item through cold test. | Supervisor and leadership | N/A
2 | Parts not packed on time | AVOID | To assure proper time, reduce time spent processing item through cold test. | Supervisor and leadership | N/A
3 | Risk to safety | MITIGATE | To assure proper time, reduce time spent processing item through cold test. | Supervisor and leadership | N/A
4
5
6
7
8
9
10
11
12
13
14
15
16