## Assumptions Log
General Assumption Log
List any project factors that you consider to be true, real, or certain. These assumptions generally involve a certain degree of risk. Describe the potential impact of these assumptions should they prove to be false.
NO. | COMPANY | ASSUMPTION | DATE | ACTIONS | RISK LEVEL | RESOLUTION
1 | HS&S | Due to previous track record of the company, HS&S does not arrive on the promised date of 7/12/2023 to conduct the training, pushing the date back a few weeks (1-3 total) | 2023-06-27 | Verify with HS&S after the holiday to make sure someone is on their way to conduct the training. If not, then select an alternate plan to measure the parts per KLA's request | 9
2 | HS&S | There could be another technical problem that arises while the company conducts training. | 2023-06-27 | Nothing to control on this end as this is an "as happens" instance. Rating is based on the probability | 7
3 | KLA | Time demand might change, which would require a change from internal measurements to external via an outside service | 2023-06-27 | A low probablility for this to happen. The longer we wait to verify this option, the more costly it will be to pay for the service (emergency charges and the like) | 6
4 | Cryowest | Agents involved in measuring the parts will not be fully trained by HS&S due to time. All efforts will involve the agents searching for programming tips and developing their own catalog as they go. | 2023-06-27 | Part of the process we would have to accept going forward with the internal measurements, but undesireable. | 11
5 | Cryowest | While cleaning the part after measuring and adjusting, the o-ring surfaces get scratched | 2023-06-27 | This has happened before and will need to be handled with care by either a quality assurance representative or a trusted production agent | 12
6 | Cryowest | While wire checking the part for KLA, it is possible to have the product not wired properly or have an issue with the wire in question. This could lead to another delay in production | 2023-06-27 | A minimal chance of it happening, but still possible the wires were damaged on their way back to Cryowest to repair. | 3
7 | Cryowest | While applying the shrink wrap to the part, there could be damages if it is not applied correctly or evenly. | 2023-06-27 | A minimal chance of it happening, but still possible. Operators have struggled before with adhering shrink wrap | 2
8 | Cryowest | While engraving with the engraving pen from shipping, the agent in question could mangle or marr the surface, making it impossible to mark. | 2023-06-27 | A minimal change of it happening. Make sure the agent has stayed away from caffiene before attempting engraving | 2
9 | Cryowest | The cases provided by KLA will not work properly after the product is altered. | 2023-06-27 | A minimal chance of it happening, but as with all things altered, it can still be an issue | 2

## Risk Management Matrix
Risk Rating Key | 0 | 1 | 2 | 3
| Acceptable - Little effect | Tolerable - Effects are felt | Undesireable - Serious impact | Intolerable - Disaster
Improbable - Risk Unlikely | Low 1 | Medium 4 | Medium 6 | High 10
Possible - Risk likely | Low 2 | Medium 5 | High 8 | Extreme 11
Probable - Risk will occur | Medium 3 | High 7 | High 9 | Extreme 12

## Risk Stats
Risk No | Count | Sums |  | Titles | How to use this section
1 | 0 | 6 |  | Average | This section aggregates all risk levels presented on the Assumption Log Tab. This is to allow a better view of all risks and assumptions categoried. The higher the risk average, the more at risk the project is overall.
2 | 3 | 4 |  | Std. Dev.
3 | 1
4 | 0 | Range | Ct | Deviations
5 | 0 | -6 | 0 | -3
6 | 1 | -2 | 0 | -2
7 | 1 | 2 | 1 | -1 | An example: If a project averages out at 6.0 with a standard deviation of 2.0, the risk is much higher than one with an average of 7.0 and a standard deviation of 0.5. This also allows the manager to figure out how to improve the risk category or accept the risk as-is.
8 | 0 | 6 | 2 | 0
9 | 1 | 10 | 2 | +1
10 | 0 | 14 | 0 | +2
11 | 1 | 18 | 0 | +3
12 | 1