## Gantt Chart
GANTT CHART TEMPLATE
PROJECT TITLE | Remaining Space-X 8 arned weld
WO Number | 12435/1
COMPANY NAME | Space-X / Cryowest
DATE | 2023-06-21
[37 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | WELDING
1.1 | ARM WELDING
1.1.1 | Weld | Sunny | 2023-06-21 | 2023-06-28 | 6 | 0%
1.1.2 | Leak Check | Rogelio | 2023-06-21 | 2023-06-28 | 6 | 0%
1.1.3 | Measure (added as of 6/21) | Max | 2023-06-22 | 2023-06-28 | 5 | 0%
1.1.3.1 | Catching up on previous measures | Max | 2023-06-22 | 2023-06-22 | 1 | 0%
1.1.4 | Wrap | Misha | 2023-06-21 | 2023-06-28 | 6 | 0%
1.1.4.1 | [Repeat until all arms are welded] | N/A [placeholder]
1.2 | END SEAMS
1.2.1 | Right end seam | Sunny | 2023-06-28 | 2023-06-28 | 1 | 0%
1.2.2 | Left end seam | Sunny | 2023-06-28 | 2023-06-28 | 1 | 0%
1.3 | END CAPS
1.3.1 | Right end cap (preassembled) | Sunny | 2023-06-28 | 2023-06-28 | 1 | 0%
1.3.2 | Left end cap (preassembled) | Sunny | 2023-06-28 | 2023-06-28 | 1 | 0%
1.4 | FRONT COLLAR
1.4.1 | Front collar plate | Sunny | 2023-06-29 | 2023-06-29 | 1 | 0%
1.5 | OTHER WELDS
1.5.1 | Weld valve lines | Sunny | 2023-06-29 | 2023-06-29 | 1 | 0%
1.5.2 | Weld gland | Sunny | 2029-06-29 | 2029-06-29 | 1 | 0%
1.5.3 | Other minor welds | Sunny | 2023-06-29 | 2023-06-29 | 1 | 0%
2 | BAKE
2.1 | BAKE PROCESS
2.1.1 | Insert in oven | Cesar | 2023-07-05 | 2023-07-10 | 4 | 0%
3 | ASSEMBLY AND COLD TESTING
3.1 | ASSEMBLY
3.1.1 | Install all valves and tubing | Cesar | 2023-07-10 | 2023-07-11 | 2 | 0%
3.2 | COLD TESTING
3.2.1 | Set up air manifolds | Cesar / Ken | 2023-07-12 | 2023-07-13 | 2 | 0%
3.2.2 | Run cold test | Cesar | 2023-07-14 | 2023-07-25 | 8 | 0%
Formulas:
DURATION = NETWORKDAYS([START],[DUE])